CITY NATURE CHALLENGE 2026: Kangra District, Himachal Pradesh, India

District-Level Action Plan

Proposed by: Himalayan Institute for Transformative Actions (HITA),

Implemented by : collaborating partners

Background

The City Nature Challenge (CNC) is a global citizen-science initiative where cities and regions document biodiversity using the iNaturalist platform. Participants record observations of wild plants, animals, insects, and fungi, contributing to global biodiversity databases.

Kangra district, located in the Himalayan foothills, possesses rich biodiversity across forests, wetlands, tea gardens, and agricultural landscapes. The challenge provides an opportunity to engage citizens, students, and institutions in documenting this biodiversity.

Objectives

- Document biodiversity across urban and peri-urban areas of Kangra district.

- Promote citizen science participation among youth, institutions, and communities.

- Create awareness about conservation and urban biodiversity.

- Generate biodiversity data that supports research and conservation planning.

- Strengthen collaboration between institutions, civil society, and the Forest Department.

Target Outcomes

| Indicator | Target |
| --- | --- |
| Participants | 800+ |
| Observations | 10,000+ |
| Species documented | 1,000+ |
| Institutions engaged | 20+ |
| Field events | 10–12 |

Key Locations

Observation activities will be conducted in the following urban clusters which are most significant, with the mentioned collaborating partners:

- Dharamshala – McLeodganj – Yol – Dharamkot belt (Partner to be finalised)

- Palampur  (Palampur Awareness Club)

- Bir belt (Deer Park)

- Nurpur – Indora – Rehan belt (Deri College)

- Dehra – Jawali – Pong Dam belt (HP FD Collaboration being finalised)

These clusters represent the largest concentrations of urban population and educational institutions, making them ideal for citizen science participation and biodiversity observation drives.

Implementation Timeline

Phase 1 – Awareness & Training

1–20 April 2026

Activities:

- Orientation workshops in colleges and schools

- Training sessions on iNaturalist

- Social media campaign

- Volunteer mobilization

Phase 2 – Observation Period

24–27 April 2026

Activities:

- Biodiversity walks

- BioBlitz events

- Citizen observation drives

- Photography-based documentation

Phase 3 – Identification Period

28 April – 10 May 2026

Activities:

- Species identification sessions

- Expert review of observations

- Data consolidation

Partners can bring together the following collaborators

- Educational institutions

- Birdwatching groups

- Eco clubs

- Local communities

- Nature photographers

A whatsapp group for Himachal has been created by CNC India Challenge team. We will use that to coordinate and plan our activities. In order to do the following information is needed.

| Name of Organisation | Name of Focal Point | Email | Cell No |
| --- | --- | --- | --- |

Please see the CNC 2026 Kangra link - https://www.inaturalist.org/projects/city-nature-challenge-2026-kangra

For further information, please reach out to us at hitatrust@gmail.com or 9820292626